iNtegrate2 Ad-hoc Committee Report

Workday software implementation for Human Resources & Finance

April 2017

- The iNtegrate2 Workday project timeline is set for a go live in October 2017

- Project is in P3 Testing. Next round of testing is User Acceptance Testing beginning in middle of June through end of July.

- GBC will be responsible for the User Acceptance Testing in June and July. Resources from the project will need to be dedicated to this testing as it is crucial decision point for the Go-Live of the project.

- Grants training will be held in Reno in the middle of May.

- GBC team’s next scheduled meeting is 04/19/2017

- Training for users is projected for August and September 2017.

- Additional work on the project, besides testing, that is currently in process- Workday Subject Matter Experts functional review with NSHE and data validation & clean up. This is in addition to the team’s regular work load of just being responsible for their functional areas in Workday and regular GBC day to day duties.

- Meeting are also being held for student employment and integrations from PeopleSoft to Workday.

- Subject Matter Expert group meetings, project check point & Integration meetings are being held weekly. Biweekly meetings continue for Points of Contact, Reporting, Security, Integrations, and Training. Monthly meetings are being held for Campus Executives Committee, Steering Committee, Change Management and Data Governance.